[image: image1.emf]
Regional CTI Secretariat Interim
Ministry of Marine Affairs and Fisheries - Government of Indonesia

Mina Bahari II Bldg, 7th Floor / Jalan Medan Merdeka Timur No. 16 / Jakarta, Indonesia

Phone: + 6221.386.0623 
Chairman:  Dr.Alex Retraubun, Vice Chairman:  Dr. Gelwyn Yusuf
First Secretary:  Eko Rudianto (mrudiant@yahoo.com), Second Secretary:  Ibnu Hadi, Third Secretary: Dr.Purwanto
Coordinator:  Darmawan (darmawan@indo.net.id)


DRAFT

DECISION DOCUMENT ON                             MONITORING & EVALUATION
Fourth Senior Official Meeting

(SOM 4)
under the

Coral Triangle Initiative (CTI – CFF)

On Coral Reefs, Fisheries and Food Security

Adopted on 21 October 2009

by the Governments of Indonesia, Malaysia,                                                             Papua New Guinea, the Philippines, Solomon Islands, and Timor-Leste 
I.  BACKGROUND
1.
Roadmap discussions on Monitoring & Evaluation
The issue of Coordination Mechanisms has received significant attention by CT6 governments over the past year
· At CCC1 (Jakarta; May 2008), CT6 governments agreed on the inclusion of Monitoring & Evaluation as a Section in the Regional Plan of Action, recognizing the importance of effective monitoring and evaluation to the success of CTI implementation program.
· At CCC2 (Honiara; September 2008), agreed to establish a working group, to be led by the Philippines, to further examine and refine the quantitative targets under each of the five goals.
· At CCC3/SOM2 (Manila; October 2008), CT6 governments agreed to establish a working group to finalize the monitoring and evaluation plan and develop a set of measureable indicators with tentative numerical targets for each indicator. Indicators will be devised for quantitative targets under goals of the Regional Plan of Action.  The working group will be comprised, but not limited to technical experts from the WorldFish Center, NGOs (TNC, CI and WWF), the Asian Development Bank and several government agencies. Framework and strategy to develop  monitoring and evaluation goals, targets and indicator have been inserted in Section VI on Monitoring & Evaluation in the draft of CTI RPOA called Manila Draft.
· At CCC4 (Manado; February 2009), the Monitoring & Evaluation Working Group (MEWG) presented results of their work covering goals, targets, indicators and pertinent information for each indicator follows in a set of tables (one table for each goal of the RPoA)
· At SOM3 (Port Moresby; March 2009), due to limited time for discussion on this issue, CT6 governments agreed to only adopt the original text of Section VI on Monitoring & Evaluation in  Manila Draft, as the Section VI for the final draft of CTI Regional Plan of Action (RPOA).  This implies that the Section VI has not accommodated results from the MEWG yet.  However, CT6 governments stated that there may be a need to revisit Section VI of the RPoA (covering Monitoring and Evaluation).

· After SOM3, monitoring & evaluation section has never been discussed on two Summit Preparatory Committee meetings (Jakarta, April 2009 and Manado, May 2009.
· This document will bring back the latest adopted Sections and the latest Working Groups’ meetings results for consideration, discussion and resolution in the SOM4.

2.  Objectives of discussion at SOM 4
The M&E Working Group is on hold until it is re-energized or reconstituted.  The M&E Working Group completed its initial tasks and provided the input to the RPoA as requested by formulating an M&E system with indicators.  There is a draft which was not included in the RPoA in its entirety.  Rather an outline of the M&E system was included but not the indicators or targets for the most part were decided upon because it was thought that until each country comes up with reasonable targets, there is not much point of putting out regional targets that do not have a sound basis of agreement.  Thus, what is needed is for the M&E Working Group to be tasked with the next task, e.g. finalizing indicators, targets and the system to track the information through a state of the Coral Triangle Report.  This will also require some support since a "state of the CT Report" would be an undertaking that requires data and coordinated effort.
 

Thus, reforming the M&E Working Group is the first decision that is needed.  Then, assigning the group several tasks as noted would set the process in motion.  The first task should be to set the baseline for the indicators and targets as formulated earlier.
 

Supporting document:

· Section VI of the CTI RPOA
· Results of the Monitoring & Evaluation Working Group (MEWG results on MonitoringEvaluation.doc).

II. DECISIONS
DECISION ME1:  Reforming the Monitoring & Evaluation Working Group.
AGREE to put Monitoring & Evaluation Working Group (MEWG) on hold 

until certain quantitative targets within RPOA have been determined.
OR

AGREE to task MEWG to develop proposal to determine quantitative targets

DECISION ME2:
Working mechanism and financing
AGREE on working mechanism and financing strategy for the WG


OR

AGREE to task MEWG to propose working and financing mechanism

























































PAGE  
2

